## Indicative PP Format
Format for submission of Indicative Annual procurement plan [STRIVE]
Name of State : Uttar Pradesh
Annual Procurement Plan for Financial Year : |  |  |  |  | 2023-03-01
Date of Approval of Annual Procurement Plan : |  |  |  |  | 2021-12-14
Approved By/Name of Approving Authority : |  |  |  |  | IMC of Balaji Private ITI
S. No. | Procurement Category | Full Name of Procuring Entity | NCVT MIS code in case of ITI (10 characters) | Name/Description of Procurement/Selection | Estimated Cost [INR] | Results Area | Procurement Mode | Applicable Procurement Rules | Use of GEM [Yes/No] | Use of eProcurement [Yes/No] | Procurement Method | Market Approach [National/ International] | Proposed Procurement Start Date | Pre-bid Conference Date [if any] | Proposed Procurement End Date | Tentative Contract Award Date | Tentative Contract Duration [Months] | Tentative Completion Date
Date [if any]
[1] | [2] | [3] | [4] | [5] | [6] | [7] | [8] | [9] | [10] | [11] | [12] | [13] | [14] | [15] | [16] | [17] | [18] | [19]
1 | Goods | BALAJI PRIVATE ITI | PR09001740 | Equipment and furniture and other goods for quality improvement | 4484000 | RA 1 | Offline | As Per State Financial Rules | No | No | Tender | National | 2022-11-15 | N/A | 2022-11-30 | N/A | 5 | 2022-11-30
2 | services | BALAJI PRIVATE ITI | PR09001740 | training of teaching and management staff | 400000 | RA 1 | Offline | As Per State Financial Rules | No | No | Direct Contract | National | 2022-11-20 | N/A | 2022-12-01 | N/A | 4 | 2022-12-01
3 | IT | BALAJI PRIVATE ITI | PR09001740 | ICT Infrastructure | 2000000 | RA 1 | Offline | As Per State Financial Rules | No | No | Tender | National | 2022-04-20 | N/A | 2022-08-20 | N/A | 4 | 2022-08-20
4 | goods | BALAJI PRIVATE ITI | PR09001740 | Purchase of books and other learning material | 300000 | RA 1 | Offline | As Per State Financial Rules | No | No | Quotattion | National | 2022-10-20 | N/A | 2022-11-20 | N/A | 4 | 2022-11-20
5 | Services and goods | BALAJI PRIVATE ITI | PR09001740 | facilities for trainers | 1400000 | RA 1 | Offline | As Per State Financial Rules | No | No | Direct Contract | National | 2022-10-20 | N/A | 2022-11-20 | N/A | 4 | 2022-11-20
6 |  |  |  | total | 8584000
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Annual Procurement Plan may be prepared on the assumption that total budget will be released
Procuring entities shall ensure that procurements are carried out as per Delegation of Financial Powers and within Categories defined as 'Eligible Expenditure' in the Operations Manual
Specifications for goods to be procured shall be as per approved specifications for that trade, approved by the Competent Authority

## Sheet1 (hidden)
S No. | Indicative Procurement Category | Results Area
1 | Goods | RA 1
2 | Services | RA 2
3 | Misc (Please Specify) | RA 3
RA 4
Use of GEM
Yes
No
Name/Description of Procurement/Selection
Details of category eg. Furniture, equipment, etc.
Market Approach
National
International